## Sheet1
Residential Project Task Critical Path - Copyright 2024, Paul F Spite
Items in bold text establish one critical path
Weeks of the Timeline | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
| 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00 | 0/00-0/00
Task Designations
Obtain Soil Borings (if needed)
Obtain Permits
Final Selections
Product Lead Times
Estimates from Subcontractors
Establish Project Timeline
Obtain Needed License Data
Tree Removal
Locate Building
Rough Excavation
Soil Poisoning (if needed)
Driveway Base
Set Dumpster
Form and Pour Footings
Set Concrete Forms
Check Forms
Pour Foundation Walls
Sub-slab Preparation
Radon Reduction Below (if needed)
Sub-slab Plumbing
Concrete Slabs
Designate Staging
Framing Material Delivery
Framing
Roofing Material Delivery
Roofing
Temporary Power
Door / Window Delivery
Doors and Windows
Well Installation (if needed)
Septic System Installation (if needed)
Garage Door
Site Plumbing
Siding Delivery
Siding Installation
Rough Plumbing
Extend Radon Reduction (if needed)
Rough Mechanical
Rough Electrical
Insulation
Masonry Delivery
Install Masonry
Drywall Delivery
Drywall Installation
Install Gutters
Ceiling Insulation
Exterior Concrete
Initial Painting
Install Trim
Initial Staining
Deliver Cabinets
Install Cabinets
Finish Painting
Final Excavation
Install Lawn
Install Flooring
Install Appliances
Finish Mechanical
Finish Plumbing
Finish Electrical
Install Landscaping
Bathroom Accessories
Final Cleaning
Painting Touch-up
Dumpster Removal
Punch List Generation
Punch List Corrections
Project Closeout
Project Closing